## ProjectTeam
Name | GitHub Alias | Shorthand | Role
Dénervaud Natalya | denen1 | denen1 | developper
Kirupananthan Kaurisanker | kirku2 | kiruk2 | developper
Meyer Remo | meyer5 | meyer5 | developper
Pelts Dmytriy | Dpelts | peltd1 | scrum master
Rodriguez Ugolini Julian | chul14n | rodrj3 | developper

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original (h) | Effort Plan Updated (h) | Effort Actual (h) | Status
1 | Login in App | User should be able to log in with a given username and password | low | 4 | 4 | 0 | work in progress
2 | Patient settings | The doctor should be able to create a patient and give him different options or data. This should also be stored | high | 17 | 20 | 20 | work in progress
3 | Navigation | The doctor should be able to search for patients | high | 15 | 11 | 19 | work in progress
4 | Statistik | The doctor should see all the entries of a patient | high | 30 | 21 | 19 | work in progress
5 | Alarm system | The doctor should receive different alarms triggered by the patient | medium | 0 | 0 | 0 | waiting
6 | Create entry | The patient should be able to create an entry | high | 27 | 34 | 34 | work in progress
7 | Trigger alarm | The patient should be able to trigger different alarm types | medium | 0 | 0 | 0 | waiting
8 | Dairy Manager | When the patient sends an entry, it should be processed by a server, stored and should update the statistik | high | 0 | 0 | 0 | work in progress
|  |  | Total | 93 | 90 | 92

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original (h) | Effort Plan Updated (h) | Effort Actual (h) | Status
1 | 3 | Login in App | User should be able to log in with a given username and password |  |  |  | low | 4 | 4 | 0 | work in progress
1.1 | 3 | Create project | Create new vaddin project | All |  |  |  | 0 | 0 | 0 | waiting
1.2 | 2 | Create UI | Creating a username and password input with confirmation button | UI | rodrj3 |  |  | 4 | 4 | 0 | waiting
1.3 | 3 | Request | After confirming the input, a request should be send to the server if the input is valid | Presenter |  |  |  | 0 | 0 | 0 | waiting
2 | 1 | Patient settings | The doctor should be able to create a patient and give him different options or data. This should also be stored |  |  |  | high | 17 | 20 | 20 | work in progress
2.1 | 1 | Create UI | Create a site, where the doctor can create a patient | UI | kiruk2 | denen1 |  | 3 | 4 | 4 | done
2.2 | 2 | Store created patient | The data of a created patient should be stored | Persistence | meyer5 | peltd1 |  | 14 | 16 | 16 | work in progress
3 | 1 | Navigation | The doctor should be able to search for patients |  |  |  | high | 15 | 11 | 19 | work in progress
3.1 | 1 | Create search bar | A view, where the doctor can search for a patient by name | UI | kiruk2 | denen1 |  | 2 | 3 | 3 | done
3.2 | 1 | Create found list | A list of all found patients by name | UI, Presenter | kiruk2 | denen1 |  | 2 | 0 | 3 | done
3.3 | 1 | Show patient details | A view of all stored data of a patient | UI, Presenter | denen1 | rodrj3 |  | 4 | 4 | 5 | done
3.4 | 2 | Create link from list to details | If the doctor clicks on the name of the patient in the list, he should be naviagted to the patient details | Presenter | kiruk2 | peltd1 |  | 1 | 0 | 2 | done
3.5 | 2 | Search for patient | The Presenter should search in the Persistence for the patients by the given input | Persistence, Presenter | kiruk2 | peltd1 |  | 2 | 0 | 2 | done
3.6 | 1 | Daily overview | A view of all the activities and comments | UI | denen1 | kiruk2 |  | 4 | 4 | 4 | done
4 | 2 | Statistik | The doctor should see all the entries of a patient |  |  |  | high | 30 | 21 | 19 | work in progress
4.1 | 2 | Read dairy | Load dairy by a given patient | View, Persistence, Presenter | peltd1 | rodrj3 |  | 2 | 1 | 0 | done
4.2 | 2 | Show patient status | Shows the patient status over time as a graph | View, Persistence | peltd1 | rodrj3 |  | 2 | 3 | 0 | done
4.3 | 2 | Create entry list | Shows all the entries sorted by day | View, Persistence | peltd1 | rodrj3 |  | 2 | 2 | 0 | done
4.4 | 2 | Go to entry | If the doctor clicks on a entry, it shows him the whole entry | View, Presenter, Persistence | peltd1 | rodrj3 |  | 2 | 1 | 0 | done
4.5 | 2 | Create entry view | Create the page on which the doctor will see all the entry details | View | peltd1 | rodrj3 |  | 2 | 2 | 0 | done
4.6 | 2 | Show comments | Load and show the comments the doctor has made | View, Persistence | denen1 | rodrj3 |  | 3 | 3 | 3 | done
4.7 | 2 | Create comment | Create a comment section (InputField) which is going to be stored | View, Persistence | denen1 | rodrj3 |  | 3 | 3 | 3 | done
4.8 | 2 | Edit comment | A already excisting comment should be editable and stored | Presenter, Persistence | denen1 | rodrj3 |  | 3 | 3 | 3 | done
4.9 | 2 | Create avoidance strategy | Textfield for new avoidance strategy and storage | View, Presenter, Persistence | kiruk2 | rodrj3 |  | 3 | 0 | 3 | done
4.1 | 2 | Show avoidance strategies | Loads and shows all the avoidance strategies by a given patient | View, Persistence | kiruk2 | rodrj3 |  | 3 | 0 | 3 | work in progress
4.11 | 2 | Edit avoidance strategy | A avoidance strategy should be editable and stored | Presenter, Persistence | kiruk2 | rodrj3 |  | 3 | 0 | 4 | work in progress
4.12 | 2 | Show statistik for different options | Different options should be available (Dropbox) to show different statistiks (consum, health, motivation..) | View, Presenter, Persistence | peltd1 | rodrj3 |  | 2 | 3 | 0 | work in progress
5 | 3 | Alarm system | The doctor should receive different alarms triggered by the patient |  |  |  | medium | 0 | 0 | 0 | waiting
5.1 | 3 | Design alarm class | Create an alarm class with 3 different alarm types | Presenter |  |  |  | 0 | 0 | 0 | waiting
5.2 | 3 | Receive alarm | Process the received alarm | Presenter |  |  |  | 0 | 0 | 0 | waiting
5.3 | 3 | Notification | Send a notification to the doctor (E-Mail, Phone) | Presenter |  |  |  | 0 | 0 | 0 | waiting
6 | 1 | Create entry | The patient should be able to create an entry |  |  |  | high | 27 | 34 | 34 | work in progress
6.1 | 1 | Overview | Create a overview where the patient can select different pages. | UI | meyer5 | peltd1 |  | 1 | 1 | 1 | work in progress
6.2 | 1 | Page navigation | When the patient selects an option, he should be navigated to the right one | Presenter | meyer5 | peltd1 |  | 1 | 1 | 1 | work in progress
6.3 | 1 | Create entry | Create questions with label, radio buttons and input fields for the patient to fill up | UI | meyer5 | peltd1 |  | 2 | 2 | 2 | done
6.4 | 1 | Change page | The patient should be navigated to the next question after confirming the last one | Presenter | meyer5 | peltd1 |  | 2 | 4 | 4 | done
6.5 | 1 | Send input | After the patient has finished the entry, it should be send to the server after a confirmation | Presenter | meyer5 | peltd1 |  | 1 | 1 | 1 | work in progress
6.6 | 1 | Show entry status | Show the patient if he has to make an entry today | UI, Presenter | meyer5 | denen1 |  | 1 | 0 | 0 | work in progress
6.7 | 1 | Overview addiction | Show the patient his or her overview over the addiction | UI, Presenter, Persistence | peltd1 | rodrj3 |  | 4 | 6 | 6 | done
6.8 | 2 | Show addiction history | Shows the history of the addiction on a graph | UI, Presenter, Persistence | denen1 | peltd1 |  | 0 | 4 | 4 | done
6.9 | 2 | Show avoidance strategy | Show the patient possible avoidance strategies | UI, Presenter | denen1 | peltd1 |  | 4 | 4 | 4 | done
6,10 | 2 | Create avoidance strategy | The patient should be able to create his or her own avoidance strategies and store it | Presenter, Persistence | denen1 |  |  | 3 | 3 | 3 | done
6,11 | 1 | Implement basic model functionality | Implement basic model functionality | Model | rodrj3 | meyer5 |  | 8 | 8 | 8 | waiting
7 | 3 | Trigger alarm | The patient should be able to trigger different alarm types |  |  |  | medium | 0 | 0 | 0 | waiting
7.1 | 3 | Create UI | Create three different buttons at the start menu | UI |  |  |  | 0 | 0 | 0 | waiting
7.2 | 3 | Send message | Send a notification to the server with the tag of the alarm | Presenter |  |  |  | 0 | 0 | 0 | waiting
7.3 | 3 | Call | One of the alarms calls the ambulance (DO NOT TEST WITH THE REAL NUMBER!) | Presenter |  |  |  | 0 | 0 | 0 | waiting
8 | 2 | Dairy Manager | When the patient sends an entry, it should be processed by a server, stored and should update the statistik |  |  |  | high | 0 | 0 | 0 | work in progress
8.1 | 3 | Receive alarm | Process incoming alarms and redirect them to the alarm system | Presenter |  |  |  | 0 | 0 | 0 | waiting
8.2 | 3 | Receive entry | Receive entry and update dairy | Presenter |  |  |  | 0 | 0 | 0 | waiting
8.3 | 2 | Store entry | Store reveived entries by patient | Model | meyer5 |  |  | 2 | 0 | 0 | waiting
8.4 | 2 | Read entries | Read all entries per patient and put them into dairies | Model, Presenter | meyer5 |  |  | 2 | 0 | 0 | waiting
8.5 | 2 | Manage Dairys | Provide different needed functionalities for the dairy | Presenter | rodrj3 | meyer5 |  | 4 | 4 | 0 | waiting
8.6 | 2 | Search | Search by different parameters | Presenter | rodrj3 | meyer5 |  | 2 | 2 | 0 | waiting
8.7 | 2 | Sort | Provide sorting by different parameters | Presenter | rodrj3 | meyer5 |  | 2 | 2 | 0 | waiting
8.8 | 2 | Update data | Update changed data on web and store changed data | Presenter | rodrj3 | meyer5 |  | 2 | 2 | 0 | waiting